## Section 151. — MOBILIZATION

01 APR 2024 – FP-24

WFL Specification 01 APR 2024 1510010

Include the following on Alaska projects that require barging of equipment and materials to the project site.

Coordinate with the COE to determine if this SCR should be used.

Payment

### 151.03

Delete Subsections (c) and (d) and substitute the following:

**(c)** 100 percent of the pay item amount, including the paid invoice cost for barging equipment and materials to the site, less the amount paid under Subsections 151.03(a) and 151.03(b), will be paid after 10 percent of the original contract amount is earned from pay items (not including mobilization). The amount paid will not exceed 10 percent of the original contract amount, plus the paid invoice cost for barging equipment and materials to the site.

**(d)** Any portion of the pay item exceeding the amount paid under Subsection 151.03(c) will be paid after final acceptance.

WFL Specification 01 APR 2024 1510020

Include the following with MATOC projects.

Payment

### 151.03

Delete this Subsection and substitute the following:

The accepted quantities will be paid at the task order price per unit of measurement for the Section 151 pay items listed in the bid schedule. Payment will be full compensation for the work prescribed in this Section. See Subsection 109.05.

Progress payments for mobilization by the lump sum will be paid as follows:

**(a)** Bond premiums will be reimbursed from the mobilization pay item according to FAR Clause 52.232-5 Payments under Fixed-Price Construction Contracts, after receipt of the evidence of payment.

**(b)** 50 percent of the pay item amount, less the amount paid under Subsection 151.03(a), will be paid after 5 percent of the original task order amount is earned from pay items (not including mobilization). The amount paid will not exceed 5 percent of the original task order amount.

**(c)** 100 percent of the pay item amount, less the amount paid under Subsections 151.03(a) and 151.03(b), will be paid after 10 percent of the original task order amount is earned from pay items (not including mobilization). The amount paid will not exceed 10 percent of the original task order amount.

**(d)** Any portion of the pay item amount more than 10 percent of the original task order amount will be paid after final acceptance.