## Section 156. — PUBLIC TRAFFIC

01 APR 2025 – FP-24

Construction Requirements

WFL Specification 01 APR 2024 1560010

Include the following with Oregon projects.

### 156.02 Qualifications.

Delete this Subsection and substitute the following:

**Qualifications.** Provide a traffic control supervisor certified by the Oregon Department of Transportation. At least 30 days before starting work, submit documentation of appropriate certifications for approval.

WFL Specification 01 APR 2024 1560020

Include the following in projects delaying or restricting PUBLIC travel. Note: Edit as required to meet project requirements delaying or restricting PUBLIC travel.

Examples:

Accommodate traffic according to the following schedule:

 6:00 a.m. to 8:00 a.m. Open road

 8:00 a.m. to 4:00 p.m. 30 minute delays permitted

 4:00 p.m. to 5:00 p.m. Open road

 5:00 p.m. to 6:00 a.m. 30 minute delays permitted

The road may be closed from [INSERT DATE] to [INSERT DATE].

### 156.03 Accommodating Traffic During Work.

Add the following:

[INSERT REQUIREMENTS]

WFL Specification 01 APR 2025 1560030

Include the following in all projects.

Note: Edit as required to meet project requirements. Include limitations on activities which affect public travel. Cross-reference with Subsection 108.01.

### 156.06 Limitations on Construction Operations.

Delete Subsection (h) and substitute the following:

**(h)** Provide uninterrupted two-way communications between Traffic Control Supervisor, flaggers, and pilot cars. Provide two-way communications between flaggers, unless flaggers can see each other and communicate. Citizen band radios are not acceptable. Make communication devices available to the CO.

WFL Specification 01 APR 2024 1560050

Include the following in all projects. Edit as required after coordinating with the PM, COE, and Partner Agency on closure requirements for the July 4 Holiday.

Add the following:

**(j)** Do not perform construction operations that cause delays or otherwise interferes with public traffic during the following dates and times.

**(1)** From 6:00 p.m. Friday through 6:00 a.m. Tuesday for Memorial Day holiday.

**(2)** From 6:00 p.m. Friday through 6:00 a.m. Tuesday for Labor Day holiday.

**(3)** From 6:00 p.m. July 3 through 6:00 a.m. July 5 for Independence Day Holiday.

WFL Specification 01 APR 2024 1560060

Include the following when holiday work is not allowed. Coordinate with the PM, COE, and Partner Agency. Begin labeling additional paragraphs with (4).

**( )** On any other holiday listed in Subsection 101.04, unless approved by the CO.

WFL Specification 01 APR 2024 1560065

Include the following when weekend work is not allowed. Coordinate with the PM, COE, and Partner Agency.

**( )** From 6:00 p.m. Friday through 6:00 a.m. Monday, unless approved by the CO.

WFL Specification 01 APR 2024 1560070

Include the following when uneven lane elevations are not allowed (coordinate with plan detail and note).

**( )** Complete paving of adjacent traffic lanes to the same elevation by the end of each day.

WFL Specification 01 APR 2024 1560080

Include the following if there will be part-width construction requiring flaggers and/or pilot cars.

**(k)** For purposes of facilitating traffic, perform grading or surfacing part-width at a time. Make the width not under construction available to public traffic under alternate one-way control. Furnish pilot car and driver, or flaggers, or both, as ordered by the CO, to direct traffic through sections of road under one-way control.

WFL Specification 01 APR 2025 1560090

Include the following on all projects. Edit as required.

### 156.08 Traffic Control Supervisor.

Add the following:

**(k)** Transport personnel, construction signs, barricades, drums, cones, tubular markers, and other traffic control devices.