## Instructions
INFLATION COMPUTATION INSTRUCTIONS
30% Milestone
1 | Develop unit prices in Masterworks applying the '2.0 National Hwy CCI' inflation factor to bring the prices to current dollars. Determine the total of bid items, not including any contingencies.
2 | Complete the computation form on the tab 'Computation'. Calculation table will automatically populate with values from the highlighted cells. Rows may need to be added or deleted.
3 | Add the inflation contingency calculated in the form to Masterworks using bid item '99920-0000 DESIGN CONTINGENCY' with a supplemental description of '(INFLATION)'.
4 | Save this file within the Engineers Estimate-Prices-UPA folder in ProjectWise. Print the form to PDF and provide with 30% QC review.
70% Milestone
1 | Update all unit prices in Masterworks by incorporating any new bid information and and applying inflation to bring the prices to current dollars. Determine the total of bid items, not including any contingencies.
2 | Update the computation form on the tab 'Calculation'.
3 | Update '99920-0000 DESIGN CONTINGENCY (INFLATION)' to the new inflation contingency value.
4 | Save this file within the Engineers Estimate-Prices-UPA folder in ProjectWise. Print the form to PDF and provide with 70% QC review.
95% Milestone
1 | Remove previously applied inflation contingency from the estimate.
2 | Update all unit prices in Masterworks by incorporating any new bid information and and applying inflation to bring the prices to current dollars.
3 | Manually apply the total percent inflation to each bid item unit price in Masterworks to account for inflation from the present to the time of award.
4 | Save this file within the Engineers Estimate-Prices-UPA folder in ProjectWise. Print the form to PDF and provide with 95% QC review.

## Computation
U.S. Department of Transportation
Federal Highway Administration
ENGINEER'S ESTIMATE INFLATION COMPUTATION
PROJECT NO. |  |  |  | MILESTONE
Project XXX-X(X) |  |  |  | Milestone
PROJECT MANAGER |  |  | SCHEDULE
Name |  |  | Schedule
DESIGNER |  |  | CHECKER
Name |  |  | Name
| ENGINEER'S ESTIMATE DATE |  | ESTIMATED TOTAL OF BID ITEMS EXCLUDING CONTINGENCIES
| PROJECTED AWARD DATE |  | HISTORIC ANNUAL INFLATION
4%
TOTAL PERCENT INFLATION
CALCULATIONS
Begin Date | End Date | Inflation Rate | # Months Projecting | Inflation Contingency | Inflated Estimate1
4%
4%
4%
4%
|  |  | INFLATION CONTINGENCY | 0
1 The inflated estimate value does not include general design contingencies. The total estimated cost may be greater than what is shown.