## WFLHD471
CONTRACTOR QUALITY CONTROL PLAN
| Work Feature: | [5 empty] | WFLHD FORM 471M
Bid items associated with the work:
| Is a WFLHD 470 required for this feature of work? |  | Yes | No
Add pages (attachments) as necessary.
|  | PRE-WORK |  |  | PRODUCTION/POST-WORK
|  | Who will perform the task? | What will be done to accomplish the task? | When and where will activities be performed and at what frequency? | Date completed. | QC Reports - As quality control activities (1) thru (9) are performed, provide reports of activities including discussions, reviews, inspections, measurements and testing results. Include deficiencies encountered and description of corrective actions completed. See 153.04(b)(1)
PREPARATORY QC ACTIVITY 1 | Independently and with contractor staff review contract rquirements plans and specifications.
PREPARATORY QC ACTIVITY 2 | Check and verify submittals, plans and materials certifications for contract requirements and submit to FHWA Provide statement and signature of verification.
PREPARATORY QC ACTIVITY 3 | Check site conditions for constructability, including staging, disposal and storage areas. Identify potential quality control issues. Verify the materials delivered to the site conform to accepted materials certifications, submittals, plans and contract requirements.
PREPARATORY QC ACTIVITY 4 | Review construction staking to assure accuracy and sufficiency at each stage of construction. |  | Provide attachment
PREPARATORY QC ACTIVITY 5 | Complete operational work plan. Provide brief written narrative of the work activity describing methods, locations, crews, equipment and processes that will be used to complete the work. |  | Provide attachment
START UP QC ACTIVITY 6 | Conduct pre-work meeting. Review contract requirements jointly with construction crew, foremen and FHWA personnel prior to beginning work.
PRODUCTION QC ACTIVITY 7 | Verify that the ongoing construction will result in the end product meeting the contract requirements. Verify by inspecting, measuring and testing. |  | Provide attachment |  |  | Final Report - As quality control activities (1) thru (9) are completed document dates completed and final descriptions of results or issues associated with the QC activities in the remaining columns. See 153.04(c)
PRODUCTION QC ACTIVITY 8 | Provide immediate presence to communicate status of work to FHWA personnel and contractor personnel for quality control issue resolution.
COMPLETION QC ACTIVITY 9 | Verify completed work meets contract requirements. Implement form WFLHD 470 Notification of Completion of Work as required.
| PRE-WORK |  |  | POST-WORK
| Contractor Quality Control Manager Signature |  |  | Contractor Quality Control Manager Signature
| Approval ______________________________________ | Date__________________________ |  | Completed _____________________________ | Date__________________
| FHWA Signature |  |  | FHWA Signature
| Accepted________________________________________ | Date__________________________ |  | Accepted_______________________________ | Date_________________
*Grayed areas are not not required to be completed.