## WFLHD471
CONTRACTOR QUALITY CONTROL PLAN CHECKLIST
| Work Feature: | [5 empty] | WFLHD FORM 471CHKLST
Bid items associated with the work:
| Is a WFLHD 470 required for this feature of work? |  | Yes | No
QC Plan Activity Considerations
|  | QC TASKS | Who? will accomplish the task | What? Will be done to accomplish the task | When, where and frequency will the task be accomplished? | Narrative guidance of quality control tasks
PREPARATORY QC TASK | Independently and with contractor staff review contract rquirements plans and specifications. |  |  |  |  | Assign QC individuals to be fully knowledgeable of the contract requirements. Use this individual to act as a resource for project staff to assist in determining requirements of the work. Knowledge of requirements will improve decision making for project staff allowing maximum performance and efficiency in completing work requirements.
PREPARATORY QC TASK | Review construction staking to assure accuracy and sufficiency at each stage of construction. |  |  |  |  | Completing a systematic check on construction staking to ensure sufficiency and accuracy can save costly delays and expensive rework because of inaccurate survey. Develop a cross check method to ensure that layout and staking is correct and appropriate for the work. Develop an understandings of the information that will be conveyed by the staking.
PREPARATORY QC TASK | Complete operational work plan. Provide brief written narrative of the work activity describing methods, locations, crews, equipment and processes that will be used to complete the work. |  |  |  |  | Developing a work plan ahead of time is key to efficient performance. Sharing that knowledge in written form is instrumental in obtaining cost efficient performance. Sudden changes in work plan and methods due to oversight of essential requirements can be fatal to cost efficiency.
START UP QC TASK | Conduct pre-work meeting. Review contract requirements jointly with construction crew, foremen and FHWA personnel prior to beginning work. |  |  |  |  | Keeping the crew and the FHWA staff informed of methods, special considerations and expectations developed in the operational workplan is critical to a successful operation. Good communication should lessen misunderstood job requirements, inefficiency and re-work.
PRODUCTION QC TASK | Verify that the ongoing construction will result in the end product meeting the contract requirements. Verify by inspecting, measuring and testing. |  |  |  |  | Self inspection of initial, production and followup work phases should be defined to ensure that work is meeting requirements as it is performed. This is an essential part of quality control to verify that the product meets contract requirements. It should include visual inspections, verification measurements and testing. When deficiencies are found, establish criteria for preventing recurrences.
| Development Review |  | Post Work Evaluation
| Consider the above qc tasks and activities in the development of quality control plans |  | Consider effectiveness of QC plan, operations and documentation on the outcomes of quality and cost to improve processes, planning and cost effectiveness for future work.
| Contractor Quality Control Manager |  | Item completed
| Approval ______________________________________ | Date__________________________ | Date________________________