## Checklist
Construction EEBACS Getting Started (quick reference guide)
Task | User
| PE | Inspector | Office Staff | COE | Contractor
Acquisition Promotes to Construction | x
Construction (COE) send EEBACS User Account forms to Contractor prior to pre-con. [See Special Contract Requirement 108.01] |  |  | x | x
Forward signed User Account Forms to Local IT Service desk to add new EEBACs accounts [Section 1.1] |  |  | x | x
Review Construction Core Data and Zero Progress Payment [Sections 4.6.1.1, 4.6.3.1 ] |  |  | x
- If Acquisition and Estimate data incorrect/incomplete – send back to Acquisitions |  |  | x
Add Project Team members [Section 4.5] |  |  | x
Check Accounts [Section 4.4.1] | x |  | x | x
- Update Delphi numbers if needed | x |  | x
- If new accounts required go to Construction Modification Process/Tab | x
- Chain new accounts if necessary | x |  | x
Enter initial Contract Status [Section 4.6.1] | x
Enter Subcontractor as necessary [Section 4.6.4] | x | x |  |  | x
Enter Labor/Equipment as necessary [Section 4.6.5] | x | x |  |  | x
IDRs/CDRs (Daily Reports tab) [Section 4.6.6] | x | x |  | x | x
- Add new IDR/CDR | x | x |  | x | x
- Submit to PE | x | x |  | x | x
- PE approves/rejects (add review comments, if necessary) | x |  |  | x
Daily Diary [Section 4.6.7] | x |  |  | x
- Fill-in & sign | x |  |  | x
Add 1st Progress Payment (automatically sends you to Grand Summary tab) [Section 4.6.3.2] | x |  | x | x
Grand Summary Tab [Section 4.6.3.3] | x | x | x | x | x
- Edit Progress Payment Period as necessary (Use Period tab) [Section 4.6.3.7] | x | x | x | x
- Add Non-CM Pay items as necessary (Use Non CM Pay Item Tab) [Section 4.6.3.6] | x | x | x | x
- Add Pay Notes [Section 4.6.3.4] | x | x | x | x | x
- - Submit to PE (edit icon, automatically brings you to paynote tab) Brown circle | x | x | x | x | x
- - PE Approve Pay Notes (edit icon, automatically brings you to paynote) tab) after PE approves Pay notes Green circle | x |  | x
- - PEs, Inspectors, Contractor should all be periodically checking status of pay notes (checking for submissions, approvals, and rejections) | x | x | x | x | x
- - Add Pay notes to Pay Note Summary (click green circle or go to Pay Note Summary Tab) | x | x | x | x | x
- Pay Note Summary [Section 4.6.3.5]
- - Add Pay Item Specific Retent | x |  | x | x
- - Edit probables | x |  | x | x
- - Add to Payment (circle turns blue when Pay Item Summary has been completed) | x |  | x | x
- Once items that have had pay note activity have a blue circle (pay items with no pay note activity will remain as white circles – no pay notes for that item), Send Progress Payment to Main Office [section 4.6.3.8] | x |  | x | x
- If necessary, Construction Admin or project COE can then do 12.a through 12.c OR send back to PE to fix. (Consult Division procedures). |  |  | x | x
- Progress Payment tracking tab – fill in dates as they occur [Section 4.6.3.9] |  |  | x | x
- Progress Payment gets permanently locked after Actual Payment Date in Progress tracking is filled in [Section 4.6.3.9]
- Add new progress pay period, go back to top of 12. [Section 4.6.3.2] | x |  | x | x
Contract Modification tab (can occur at any time) [Section 4.6.9] | x | x | x | x
- Fill in general CM data | x | x | x | x
- After saving general CM data, Add Issues to add time/pay items (button appears on far right) | x | x | x | x
- Obligate/deobligate funds | x | x | x | x
Claims tab (can occur anytime) [Section 4.6.8] | x |  | x | x
- Fill in data | x |  | x | x
Finalize Contract see Contract Status Page [Section 4.6.2.1] | x |  | x | x
- Fill in dates as appropriate | x |  | x | x
Archive Project Team Members as appropriate (see Team Tab) [Section 4.5.2] |  |  | x
Send User Account form to IT to disable Contractor EEBACS account | x |  | x | x